## Sheet1
Communications and Radar-Supported Transportation Operations and Planning (CAR-STOP)
Lead for each task
Task | Subtask | Workpackage | Lead
Task 1 Conceptual and Functional Framework for Integrating Communications and Radar Overall Lead for Task 1: Joydeep Ghosh | 1.1 Develop improved collision detection and avoidance algorithms for cars | 1.1.1 Combining information from the communication and radar systems | Robert Heath
|  | 1.1.2 Incorporating vehicular dynamics and driver behavior | Chandra Bhat
| 1.2 Develop improved collision detection and avoidance algorithms between cars and non-motorized road users (bicycles and pedestrians) | 1.2.1 Incorporating radar signals to computer vision oriented methods for pedestrian and bicycles detection | Joydeep Ghosh
|  | 1.2.2 Designing a V2V communication strategy to improve CW/CA algorithms | Robert Heath
| 1.3 Dealing with uncertainty (caused, for example, by delays in the communication and inconsistency in data sources) and harnessing the power of collective intelligence | 1.3.1 Developing statistical models for the different types of uncertainty | Joydeep Ghosh
|  | 1.3.2 Introducing reliability and availability of data into the decision making process | Joydeep Ghosh
|  | 1.3.3 Collective intelligence: A principled framework for distributed decision making | Joydeep Ghosh
Task 2 Developing Joint Automotive Radar and Communication at the mmWave Band Overall Lead for Task 2: Robert Heath | 2.1: Develop a framework for joint millimeter wave communication and radar | 2.1.1: Studying the tradeoffs between radar and communication | Robert Heath
|  | 2.1.2: Designing joint waveforms and signal processing algorithms | Robert Heath
| 2.2: Optimizing the joint waveform to meet different objectives | 2.2.1: Definition of the different working scenarios | Robert Heath
|  | 2.2.2: Designing optimization strategies | Robert Heath
| 2.3: Incorporating antenna arrays | 2.3.1: Designing antenna array structures for joint radar communication units at mmWave | Robert Heath
|  | 2.3.2: Designing beamforming algorithms for joint communication and radar performance | Robert Heath
| 2.4: Dealing with security issues | 2.4.1: Using large antenna arrays to provide security at the physical layer | Robert Heath
|  | 2.4.2: Analysis of the security level in the automotive case | Robert Heath
Task 3 Conduct Preliminary Tests, Develop Concept of Operations (CONOPS), and Formulate Detailed Plans for Phase II and III Research Overall Lead for Task 3: Chandra Bhat | 3.1: Preliminary tests with real data | 3.1.1: Collect real data | Chandra Bhat
|  | 3.1.2: Simulation results using real data | Joydeep Ghosh
| 3.2: Assess benefits of proposed system and develop CONOPS | 3.2.1: Assess benefits of proposed system | ALL
|  | 3.2.2: Develop CONOPS | Chandra Bhat
| 3.3: Develop detailed Phase II and Phase III work plans | 3.3.1: Detailed plan for Phase II | Chandra Bhat
|  | 3.3.2: Detailed plan for Phase III | Chandra Bhat